## Checklist
Product Management Develop Phase Activity Checklist: Product Development and Release Checklist
Activity Group | Activity | Objectives (If Not Applicable Select "Y" for Accomplished) | Accomplished (Y/N)
Develop Phase Product Development Activities | Product Implementation | Define the lead role to manage the end-to-end product development process | Y
| Product Implementation | Identify key stakeholders required in the development phase | Y
| Product Implementation | Complete and coordinate a Develop Phase RACI | Y
| Product Implementation | Add detail to the initial Project Plan completed in the Plan phase | Y
| Product Implementation | Determine appropriate lifecycle for product development | Y
| Product Implementation | Develop required prototypes and mock-ups (As applicable) | Y
| Product Implementation | Plan hand off to manufacturing and operations | Y
| Product Implementation | Design physical packaging | N
| Product Implementation | Address issues (As applicable) | Y
| Product Requirements Refinement | Review "good enough scenario." Update Product Requirements Document (PRD) | N
| Product Requirements Refinement | Review PRD for missing requirements or lack of detail | N
| Product Requirements Refinement | Review PRD and clarify vague requirements | N
| Product Requirements Refinement | Identify and remedy implementation limitations | Y
| Product Verification Activities | Update product test strategy | N
| Product Verification Activities | Define minimum test acceptance levels | N
| Product Verification Activities | Define compliance requirements | N
| Product Verification Activities | Release product to supporting operational function | N
| Release and Configuration Management | Identify version control process | N
| Release and Configuration Management | Develop formal change management process | N
| Release and Configuration Management | Verify development and testing configurations and environments | N
| Release and Configuration Management | Manage overall product build process | N
| Release and Configuration Management | Validate final components to include packaging for distribution or operations | N
| Release and Configuration Management | Ensure all required process steps are completed | N
| Release and Configuration Management | Track defects, issues, and develop remediation plan | Y
| Release and Configuration Management | Complete product release checklist--release product | N
Issue 1: Requirements were incomplete and treated as final too early. Proposed Action: Conduct detailed requirements validation and obtain stakeholder sign-off before development. Issue 2: Multiple prototype versions caused the wrong version to be shared with the customer. Proposed Action: Use clear version control and a single approved prototype repository. Issue 3: Changes were not communicated to the entire team. Proposed Action: Use a centralized change log and require team-wide communication for all changes. Issue 4: Military compliance requirements were discovered too late. Proposed Action: Identify and validate all compliance requirements during the planning phase. Issue 5: Packaging did not meet military requirements. Proposed Action: Include compliance requirements in packaging design and validate the design before production.

## Issues Log
Current Product Development Issues
Issue | Proposed Action